## Transportation Management Plan
|  | LEVEL 4 |  |  | Project Name:
|  | TRANSPORTATION |  |  | RI Design Contract No(s):
|  | MANAGEMENT |  |  | RI Construction Contract No(s):
PLAN
[8 empty] | Submission: |  | Date:
PROJECT INFORMATION
Brief
Project
Description:
General
Work
Limits:
General
Project
Schedule*:
*The information in this section is not intended to and shall not supersede the approved schedule and milestone/completion dates for the project.
TRAFFIC-RELATED WORK RESTRICTIONS
General
Restrictions:
Holiday
Restrictions:
TEMPORARY TRAFFIC CONTROL PLANS
These RIDOT- and/or Designer-Developed TTC Plans will be used during the work on this project
[5 empty] | Included in: | [6 empty] | Included in:
RIDOT TYPICAL TTC PLANS |  |  |  |  | TMP | Plan Set |  | DESIGNER-DEVELOPED TTC PLANS |  |  |  | TMP | Plan Set
Mobile Operation
Work Beyond the Shoulder
Shoulder Closure - Two Lane Road
Shoulder Closure - Limited Access
1-Side Lane Shift - Two Lane Road
2-Side Lane Shift - Two Lane Road
PERFORMANCE MONITORING, CHANGES TO TMP, & CONTINGENCIES
The Contractor's TMP Implementation Manager (if identified below) is responsible for keeping the portion of the project being used by public traffic in a condition that (1) safely and adequately accommodates such traffic and (2) is in accordance with the Traffic-Related Work Restrictions, the Temporary Traffic Control Plans, and where appropriate, the other transportation management strategies identified above. The RIDOT TMP Implementation Manager or his/her responsible designee should (1) inspect the project work zones at initial setup, at the start of each subsequent work day, and just prior to extended breaks in the work (e.g., weekends) for conformance with the Temporary Traffic Control Plans, the ATSSA Quality Guidelines for Temporary Traffic Control Devices and Features, and where applicable, the other transportation management strategies identified above and (2) document all work zone-related feedback and complaints that are received from the public.
If at any time (1) a significant deviation from any of the strategies included in the TMP (e.g., the use of an alternate Temporary Traffic Control Plan) is desired by one or more members of the project implementation team, (2) field observations and/or data suggest that impacts to road users are or will be unacceptable, or (3) one or more performance requirements established in the TMP are not being met in the field, the RIDOT TMP Implementation Manager shall report the situation to his/her supervisor or Division/Section/Unit manager. The supervisor / manager will coordinate with the State Traffic Engineer, the Traffic Management Chief, the TMP Implementation Manager(s), the Chief Engineer, and/or other interested parties as appropriate and/or necessary to consider and determine whether revised and/or alternate strategies should be implemented in an effort to lessen the adverse safety and/or mobility impacts of the project. If the supervisor / manager deems that strategy changes should be implemented, the changes shall be documented in a revised version of the TMP and the Traffic Management Chief, the State Traffic Engineer, and the Chief Engineer must approve of the revised TMP prior to their implementation.
If a significant deviation from any of the strategies included in the TMP is requested by the Contractor, unless directed otherwise by the RIDOT the Contractor is responsible for preparing and submitting to the RIDOT TMP Implementation Manager appropriate documentation (e.g., design calculations, analysis reports, Temporary Traffic Control Plans, etc.) showing that the requested change(s) are (1) feasible and (2) expected to result in safety and mobility impacts that are no more adverse than the impacts resulting from the strategies already included in the latest approved TMP. The RIDOT will review and consider the submittal(s) as described in the preceding paragraph and will determine whether the changes should be implemented. If the requested changes are approved by the RIDOT, unless otherwise directed by the RIDOT the Contractor shall prepare and submit to the RIDOT TMP Implementation Manager a revised version of the latest approved TMP in both printed and electronic (Microsoft® Excel) format that documents all of the approved changes. Work to implement the changes shall not begin until the Traffic Management Chief, the State Traffic Engineer, and the Chief Engineer have approved of the revised TMP.
Other | [13 empty] | When unexpected events (e.g., crashes, inclement weather, unforeseen traffic demands, etc.) occur in a project work zone, the RIDOT TMP Implementation Manager or his/her responsible desingee shall determine whether
Requirements:
TMP APPROVALS
All approvals must be obtained prior to start of work
TRAFFIC MANAGEMENT CHIEF |  |  |  |  | STATE TRAFFIC ENGINEER |  |  |  |  | CHIEF ENGINEER
Signature: |  |  |  |  | Signature: |  |  |  |  | Signature:
Date: |  |  |  |  | Date: |  |  |  |  | Date:
Revision # |  | Initials | Date |  | Revision # |  | Initials |  | Date | Revision # | Initials | Date
TMP IMPLEMENTATION MANAGERS
Project managers with the primary responsibility & authority for implementation of this TMP
RIDOT | [7 empty] | CONTRACTOR (if contract work)
| Name: | [7 empty] | Name:
| Title: | [7 empty] | Title:
| Unit: | [7 empty] | Company/Unit:
| Office Phone: | [7 empty] | Office Phone:
| Mobile Phone: | [7 empty] | Mobile Phone:
| E-Mail: | [7 empty] | E-Mail:
|  |  | Submission List | [5 empty] | Check Box List
|  |  |  | Planning |  |  |  |  | √
Conceptual
DSR
CDR
10%
EA
EIS
30%
75%
90%
PS&E
ADV
FINAL
Constr.Rev.#1
Constr.Rev.#2
Constr.Rev.#3
Constr.Rev.#4
Constr.Rev.#5
Constr.Rev.#6
Constr.Rev.#7
Constr.Rev.#8
Constr.Rev.#9
Constr.Rev.#10
Note on F10: Guidance for Completing this Section: Provide a brief project description (may be same as the one included in the PMP, if applicable). If possible, also provide a brief list of the types of work equipment that will be used within roadway limits.
Note on F16: Guidance for Completing this Section: Summarize the general work limits. Also summarize specific traffic restrictions that are expected on major roadways during the work (e.g., shoulder closures, lane closures, lane shifts, etc.).
Note on F22: Guidance for Completing this Section: Provide a brief overview of the general work schedule including major project milestones, all based on the latest project schedule. If applicable, also briefly describe the overall recommended construction sequence.
Note on F30: Guidance for Completing this Section: With consideration of road user volumes collected/considered during design, list appropriate hours and days in accordance with procedures described in latest RIDOT Traffic Design Manual. Also specify any other traffic safety and/or mobility-related work restrictions for specific locations or roadways (e.g., no work on certain roadways when school is in session). If necessary for clarity, unmerge cells to allow for a more readable listing of dates and details to be entered.
Note on F36: Guidance for Completing this Section: With consideration of road user volumes collected/considered during design, list appropriate hours and days in accordance with procedures described in latest RIDOT Traffic Design Manual. If necessary for clarity, unmerge cells to allow for a more readable listing of dates and details to be entered.
Note on F71: Guidance for Completing this Section: If applicable, include a description of any other specific observational, logging, and/or recording activites that are required during the project for work zone performance measurement purposes (e.g., collection of volume counts, recording of queue lengths, measurement of travel times, monitoring of crashes and/or complaints, etc.). Provide the timelines/schedules and the responsible person(s) responsible for each monitoring activity. For monitoring work to be completed by the Contractor, such specific requirements must be included in Job Specific Specifications if not already included in the RIDOT Standard Specifications, and need only be referenced here. Where applicable, make reference to RIDOT policies, standards, requirements, and procedures.
Note on M2: Welcome to the RIDOT TMP Template! This document should be saved locally with the filename "Level 4 TMP - [RI Construction Contract Number(s)]" or, if there is no RI Construction Contract Number(s), "Level 4 TMP - [Project Name]". In general, and only where appropriate, cells with a yellow background color should be completed/modified by the Designer. Notes provided in comment form (as indicated by a red triangle) throughout the worksheet provide guidance in how to properly complete this Template.
Note on O3: Note: Enter RI contract number(s) if applicable, otherwise enter N/A.
Note on P4: Note: Enter RI contract number(s) if applicable, otherwise enter N/A.
Note on B97: Guidance for Completing this Section: Unless directed otherwise by the RIDOT, the Designer is not responsible for completing this section. For RIDOT construction and maintenance projects, typically this will be the Resident Engineer. For RIDOT maintenance activities, typically this will be the work supervisor from the Highway & Bridge Maintenance Division. For Temporary Traffic Control Permits, typically this will be the safety inspector assigned to the permit from the Health & Safety Section.
Note on M97: Guidance for Completing this Section: Following approval of the final TMP but prior to start of work, the Contractor with the primary responsibility and authority for implementation of this TMP shall be identified here. For RIDOT construction and maintenance projects and maintenance activities, the Designer should leave this section blank unless directed otherwise by the RIDOT. For Temporary Traffic Control Permits, the Designer is responsible for arranging for the identification of the Contractor here. (NOTE: For investigative work carried out by the Designer under approval of a Temporary Traffic Control Permit, the Designer may be the Contractor).
Note on F85: Guidance for Completing this Section: Enter the name of the appropriate RIDOT person who currently serves in this role.
Note on K85: Guidance for Completing this Section: Enter the name of the appropriate RIDOT person who currently serves in this role.
Note on Q85: Guidance for Completing this Section: Enter the name of the appropriate RIDOT person who currently serves in this role.

## Strategy List
PUBLIC INFORMATION STRATEGIES | TRANSPORTATION OPERATIONS STRATEGIES | PERFORMANCE MONITORING STRATEGIES | TRAFFIC CONTROL STRATEGIES
Team meetings
PUBLIC AWARENESS STRATEGIES | DEMAND MANAGEMENT STRATEGIES | Windshield surveys | TRAFFIC CONTROL DEVICES
RIDOT travel advisories news releases | Transit service improvements | Public surveys | Temporary construction signs
RIDOT travel advisories web site | Transit incentives | Surveillance: Traffic counts | Arrow panels
Brochures and mailers | Shuttle services | Surveillance: Traffic queues/delays | Channelizing devices - Drums
Other press releases/media alerts | Ridesharing/carpooling incentives | Surveillance: Travel times | Channelizing devices - Cones
Paid advertisements | Park-and-ride promotion | Surveillance: Crash data | Channelizing devices - Barricades
Public information center | High-occupancy vehicle (HOV) lanes | Assessment: Mobility | Channelizing devices - Tubular markers
Dedicated telephone hotline | Toll/congestion pricing | Assessment: Safety | Linear Delineation Panels
Dedicated project web site | Ramp metering | Road safety audits (construction) | Temporary pavement markings
Public meetings/hearings | Parking supply management |  | Trafficpersons
Community task forces | Variable work hours |  | Flagpersons
Consultation/coordination w/ stakeholders | Telecommuting |  | Temporary traffic signals
Work zone education and safety campaigns |  |  | Lighting devices
Rideshare promotions
Supplemental visual information
CORRIDOR/NETWORK MANAGEMENT STRATEGIES
Signal timing/coordination improvements
Street/intersection improvements
ROAD USER INFORMATION STRATEGIES | Bus turnouts
RIDOT 511 traveler information system | Turn restrictions
Commercial radio traffic reports | Parking restrictions
Changeable message signs (CMS) | Truck/heavy vehicle restrictions
Dynamic driver feedback speed display sign | Separate truck lanes
Highway advisory radio (HAR) | Reversible lanes
Highway information network (web-based) | Dynamic lane closure system
Freight travel information | Ramp metering
Railroad crossing traffic control
WORK ZONE SAFETY MANAGEMENT STRATEGIES
Speed limit reduction/variable speed limits
Temporary traffic barrier
Movable traffic barrier systems
Crash attenuators
Temporary rumble strips
Intrusion alarms
Warning lights
Automated Flagger Assistance Devices(AFADs)
Project safety task force/committee
Road safety audits (design)
Project on-site safety training
Safety awards/incentives
TRAFFIC/INCIDENT MANAGEMENT & ENFORCEMENT STRATEGIES
Dedicated project work zone ITS
RIDOT Transportation Management Center
Helicopter for aerial surveillance
Traffic screens
Location reference markers
Tow/freeway service patrol
Survey equipment for major incidents
Photogrammetry for major incidents
Establish available local detour routes
Contract support for incident management
Incident/emergency management coordinator
Incident/emergency response plan
Dedicated (paid) police enforcement
Cooperative police enforcement
Automated enforcement

## Implementation Costs
| Project Name: |  |  |  | RIC No(s).
| Submission: |  | Date:
TMP IMPLEMENTATION COST ESTIMATES
Temporary Traffic Control Devices / Personnel
ITEM |  | EST. COST |  | ITEM |  |  |  | EST. COST
[6 empty] | Total Temporary Traffic Control Device/Personnel Estimated Cost: | 0
Public Information Plan Strategies
ITEM |  | EST. COST |  | ITEM |  |  |  | EST. COST
[6 empty] | Total Public Information Plan Implementation Estimated Cost: | 0
Transportation Operations Plan Strategies
ITEM |  | EST. COST |  | ITEM |  |  |  | EST. COST
[6 empty] | Total Transportation Operations Plan Implementation Estimated Cost: | 0
Performance Monitoring Plan Strategies
ITEM |  | EST. COST |  | ITEM |  |  |  | EST. COST
[6 empty] | Total Performance Monitoring Plan Implementation Estimated Cost: | 0
[6 empty] | TOTAL TMP IMPLEMENTATION COST: | 0
Notes
[9 empty] | PUBLIC INFORMATION STRATEGIES | TRANSPORTATION OPERATIONS STRATEGIES | PERFORMANCE MONITORING STRATEGIES | TRAFFIC CONTROL STRATEGIES
Team meetings
[9 empty] | PUBLIC AWARENESS STRATEGIES | DEMAND MANAGEMENT STRATEGIES | Windshield surveys | TRAFFIC CONTROL DEVICES
[9 empty] | RIDOT travel advisories news releases | Transit service improvements | Public surveys | Temporary construction signs
[9 empty] | RIDOT travel advisories web site | Transit incentives | Surveillance: Traffic counts | Arrow panels
[9 empty] | Brochures and mailers | Shuttle services | Surveillance: Traffic queues/delays | Channelizing devices - Drums
[9 empty] | Other press releases/media alerts | Ridesharing/carpooling incentives | Surveillance: Travel times | Channelizing devices - Cones
[9 empty] | Paid advertisements | Park-and-ride promotion | Surveillance: Crash data | Channelizing devices - Barricades
[9 empty] | Public information center | High-occupancy vehicle (HOV) lanes | Assessment: Mobility | Channelizing devices - Tubular markers
[9 empty] | Dedicated telephone hotline | Toll/congestion pricing | Assessment: Safety | Linear Delineation Panels
[9 empty] | Dedicated project web site | Ramp metering | Road safety audits (construction) | Temporary pavement markings
[9 empty] | Public meetings/hearings | Parking supply management | 0 | Trafficpersons
[9 empty] | Community task forces | Variable work hours | 0 | Flagpersons
[9 empty] | Consultation/coordination w/ stakeholders | Telecommuting | 0 | Temporary traffic signals
[9 empty] | Work zone education and safety campaigns | 0 | 0 | Lighting devices
[9 empty] | Rideshare promotions | 0 | 0 | 0
[9 empty] | Supplemental visual information | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 | 0 |  | 0
[9 empty] | 0 |  |  | 0
[9 empty] | 0 | CORRIDOR/NETWORK MANAGEMENT STRATEGIES |  | 0
[9 empty] | 0 | Signal timing/coordination improvements |  | 0
[10 empty] | Street/intersection improvements |  | 0
[9 empty] | ROAD USER INFORMATION STRATEGIES | Bus turnouts |  | 0
[9 empty] | RIDOT 511 traveler information system | Turn restrictions |  | 0
[9 empty] | Commercial radio traffic reports | Parking restrictions
[9 empty] | Changeable message signs (CMS) | Truck/heavy vehicle restrictions
[9 empty] | Dynamic driver feedback speed display sign | Separate truck lanes
[9 empty] | Highway advisory radio (HAR) | Reversible lanes
[9 empty] | Highway information network (web-based) | Dynamic lane closure system
[9 empty] | Freight travel information | Ramp metering
[9 empty] | 0 | Railroad crossing traffic control
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
0
WORK ZONE SAFETY MANAGEMENT STRATEGIES
Speed limit reduction/variable speed limits
Temporary traffic barrier
Movable traffic barrier systems
Crash attenuators
Temporary rumble strips
Intrusion alarms
Warning lights
Automated Flagger Assistance Devices(AFADs)
Project safety task force/committee
Road safety audits (design)
Project on-site safety training
Safety awards/incentives
0
0
0
0
0
TRAFFIC/INCIDENT MANAGEMENT & ENFORCEMENT STRATEGIES
Dedicated project work zone ITS
RIDOT Transportation Management Center
Helicopter for aerial surveillance
Traffic screens
Location reference markers
Tow/freeway service patrol
Survey equipment for major incidents
Photogrammetry for major incidents
Establish available local detour routes
Contract support for incident management
Incident/emergency management coordinator
Incident/emergency response plan
Dedicated (paid) police enforcement
Cooperative police enforcement
Automated enforcement
0
0
0
0
0
Note on B6: Guidance for Completing this Section: Where feasible, provide itemized cost estimates for each of the selected TTC Devices (as shown on TTC Plans) and Personnel, PI strategies, TO strategies, and PM strategies that are to be funded under a contract for the project. For strategies to be completed by the Contractor as part of the construction contract, these costs will be the same as those included in the Engineer's Estimate. Note that TMP strategies to be implemented by the RIDOT (e.g., a coordination effort or use of the TMC) should not be listed here if the strategy is to be carried out and "funded" as part of normal RIDOT operating procedure. However, new, special, and/or project-specific activites should be listed and a cost estimate provided (e.g., a dedicated project web site is developed by a Consultant).
Note on B53: Guidance for Completing this Section: Describe any special notes, including (where applicable) any cost sharing or coordination with other projects/municipalities.

## Post-Construction Assessment
TRANSPORTATION MANAGEMENT PLAN
POST-CONSTRUCTION WORK ZONE PERFORMANCE ASSESSMENT
This assessment shall be completed by the RIDOT TMP Implementation Manager upon completion of the work to document lessons learned and provide recommendations on how to improve the TMP process and/or modify guidelines. The responses should allow the reviewer of this completed Assessment to understand the successes/failures of the project TMP itself and its requirements.
Describe Areas of the TMP that were Most Successfully Implemented & Why
Describe Areas of the TMP that were Least Successfully Implemented & Why
Summarize/Describe all Changes Necessary to Correct Oversight of the Original TMP
Summarize the Effectiveness of Each Change Made to the TMP
Summarize the Type and Frequency of Legitimate Complaints Received
Describe/Summarize Road User Mobility Impacts Observed During Work
Describe/Summarize Crashes and Incidents that Occurred During the Work
Describe/Summarize Road Safety Impacts Observed During Work
Suggested TMP Improvements or Changes for Future Similar Projects
This completed assessment shall be forwarded to the Chief Engineer following approval below.
RIDOT TMP Implementation Manager Approval
Name:
Title:
Unit:
Signature:
Date: